## Template
Step | Task | Subtasks | Task Cost Estimate | Staff Hours | Expenses | Volunteer time | Budget Notes
1. Evaluation Scope and Clarification of the Problem | 1a: Scoping | Scoping workshop, internal meetings
| 1b: Workplan and budget | Develop detailed workplan, Create budget forecast
2. Understand the Context | 2a: Define inputs | Identify program inputs per scope
| 2b: Program Cost | Calculate program input costs
| 2c: Define “Who” | Stakeholder and partners mapping, Inclusion strategies, internal meetings
3. Identify Program Benefits | 3A: Identify Change | Internal workshops, Stakeholder and partners workshop on program benefits
| 3B: Organize Benefits | Sort benefits into means and ends, Prioritization session
| 3C: Timescale of Benefits Matrix | Create matrix, Timeline planning
4. Measure Changes | 4A: Characterizing the Change | Internal meetings, interviews, data collection
| 4b: Simple Attribution | Attribution modeling, Cause-effect analysis
5. Valuing the Change | 5a: Identify who will be involved in the weighting process | Define stakeholder and partners roles
| 5b: Generate value weights | Develop valuation tool, Weighting metrics, Weighting workshop/interviews
6. Calculate Value and ROI | 6a: Translate Benefits | Monetize program benefits, Develop models
| 6b: Calculate ROI | ROI analysis, Report development
7. Validate Results
8. Communication | 8a. Reporting Template | Develop communication strategy, Material creation | 8000 | 83 | 3000 | 54 | Graphic designer, writer fees, and materials
TOTAL

## Example
Step | Task | Subtasks | Task Cost Estimate | Staff Hours | Expenses | Volunteer time | Budget Notes
1. Project Scope and Clarification of the Problem | 1a: Scoping | Scoping workshop, internal meetings | 2000 | 30 | 200 | 20 | Workshop facilitation and materials, Staff and volunteer time
| 1b: Workplan and budget | Develop detailed work plan, Create budget forecast | 1500 | 25 | 0 | 16 | Staff and volunteer time for development and documentation
2. Understand the Context | 2a: Define inputs | Identify program inputs per scope | 1500 | 25 | 0 | 16 | Staff and volunteer time
| 2b: Program Cost | Calculate program input costs | 4000 | 67 | 0 | 44 | Staff and volunteer time
| 2c: Define “Who” | Stakeholder and partners mapping, Inclusion strategies, internal meetings | 2000 | 33 | 0 | 21 | Staff and volunteer time
3. Identify Program Benefits | 3A: Identify Change | Internal workshops, Stakeholder and partners workshop on program benefits | 3500 | 50 | 500 | 33 | Workshop facilitator and materials
| 3B: Organize Benefits | Sort benefits into means and ends, Prioritization session | 1500 | 25 | 0 | 16 | Staff and volunteer time
| 3C: Timescale of Benefits Matrix | Create matrix, Timeline planning | 1000 | 17 | 0 | 11 | Staff and volunteer time
4. Measure Changes | 4A: Characterizing the Change | Internal meetings, interviews, data collection | 4000 | 50 | 1000 | 33 | Facilitation and stakeholder and partners engagement, mileage/travel, Staff and volunteer time
| 4b: Simple Attribution | Attribution modeling, Cause-effect analysis | 3500 | 58 | 0 | 38 | Staff and volunteer time
5. Valuing the Change | 5a: Identify who will be involved in the weighting process | Define stakeholder and partners roles | 1000 | 17 | 0 | 11 | Staff and volunteer time
| 5b: Generate value weights | Develop valuation tool, Weighting metrics, Weighting workshop/interviews | 2500 | 28 | 800 | 18 | Tool development and stakeholder and partners input, Staff and volunteer time
6. Calculate Value and ROI | 6a: Translate Benefits | Monetize program benefits, Develop models | 4500 | 42 | 2000 | 27 | Staff and volunteer time, outside expert support for legitimacy
| 6b: Calculate ROI | ROI analysis, Report development | 3000 | 17 | 2000 | 11 | Staff and volunteer time, outside expert support for legitimacy
7. Validate Results
8. Communication | 8a. Reporting Template | Develop communication strategy, Material creation | 8000 | 83 | 3000 | 54 | Graphic designer, writer fees, and materials
|  | TOTAL | 43500 | 567 | 9500 | 369